## Sprint1
TEAM 11 - SPRINT BACKLOG
RF-Robertson Filho |  | NOT STARTED
IN PROGRESS
COMPLETED
Monday 14th July - Wednesday 23th July
Sprint 1 - TASK DESCRIPTION | Allotted time (hrs) | Status | Mon | Tue | Wed | Thu | Fri | Mon | Tue
1.1 Project preparation
Look for backup chart library for android | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0
Study android server setup | 5 |  | 5 | 4 | 3 | 10 | 10 | 10 | 10
Uploading any changes to gitHub | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 Coding
select/open class activity | 3 |  | 2 | 2 | 2 | 1 | 1 | 1 | 1
select/open class xml | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
create/register classes activity | 5 |  | 5 | 5 | 5 | 4 | 3 | 0 | 0
create/register classes xml | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0
create tabs for multiple graphs in results activity | 8 |  | 8 | 6 | 6 | 6 | 6 | 6 | 6
1.3 Testing
Exploratory testing | 3 |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
Spring 2: Total Hours remaining | 31 |  | 26 | 20 | 16 | 21 | 20 | 17 | 17

## Sprint2
TEAM 11 - SPRINT BACKLOG
RF-Robertson Filho |  | NOT STARTED
IN PROGRESS
COMPLETED
Monday 14th July - Wednesday 23th July
Sprint 1 - TASK DESCRIPTION | Allotted time (hrs) | Status | Mon | Tue | Wed | Thu | Fri | Mon | Tue
1.1 Project preparation
Study android server setup | 8 |  | 8
Talk with Mahamadou to fix gitHub | 2 |  | 2
1.2 Coding
create tabs for multiple graphs in results activity | 8 |  | 5
create JSON sender for student activity | 4 |  | 1
set up a database to store answers in the school of computing servers | 5 |  | 5
transform and read the JSON for the chars | 4 |  | 4
1.3 Testing
Exploratory testing | 3
Spring 2: Total Hours remaining | 34 |  | 25 | 0 | 0 | 0 | 0 | 0 | 0